## name of sheet
input box | output box
All indications and formulae without engagement. | © Controllinglexikon.de
Planned Value
Name: | Planned Value
Question: | What is a planned value of a project
Formula:
Measure: | Planned value is expressed as a Currency Eg: Dollars or Euros. Planned % complete as a percentage, BAC as a Currency
Example:
Investigation/Derivation: | Duration of the project, time elapsed, percentage completed and the project cost are used to determine the planned value of a project.
Notice: | It is the value that you should have been earned as per the schedule.
Related Key Performance Indicators: | PV is used in determing schedule variance and schedule performance index
Calculator
Planned%completed | 50%
*
BAC | 1000000
PV | 500000
Source: | https://pmstudycircle.com/2012/05/planned-value-pv-earned-value-ev-actual-cost-ac-analysis-in-project-cost-management-2/
Author: | Mohammad Almohtaseb
Planned Value
Planned Value=𝑷𝒍𝒂𝒏𝒏𝒆𝒅 % 𝑪𝒐𝒎𝒑𝒍𝒆𝒕𝒆 × 𝑩𝒖𝒅𝒈𝒆𝒕 𝒂𝒕 𝑪𝒐𝒎𝒑𝒍𝒆𝒕𝒊𝒐𝒏 (𝑩𝑨𝑪)
Planned Value
Planned Value=𝟓𝟎% ×𝟏.𝟎𝟎𝟎.𝟎𝟎𝟎