## name of sheet
input box | output box
All indications and formulae without engagement. | © Controllinglexikon.de
Schedule Performance Index (SPI)
Name: | Schedule Performance Index (SPI)
Question: | What is the relationship between the value of the work done and the planned work in a project at a certain intermediate ?
Formula:
Measure: | Earned value approach is a detailed structural representation of all project activities with the corresponding, regularly updated cost, performance and time information on the progress of the project (as planned and actual values).
Example:
Investigation/Derivation: | Earned Value = Planned cost of the workload. Planned Value = Planned cost of the planned workload. The "Schedule Performance Index" measure is expressed in the unit of measure "%".
Notice: | If SPI is greater than 1, the project is ahead of schedule. If SPI is less than 1, the project is behind schedule, and if SPI is equal to 1, the project is proceeding on time.
Related Key Performance Indicators: | "Cost Performance Index (CPI)"; "To Complete Performance Index (TCPI)"; "Estimate at completion (EAC)"; Time Estimate at Completion (TEAC)
Calculator
Earned Value | 500
Planned Value | 600
Schedule Performance Index (SPI) | 83.33%
Source: | https://www.pmlearningsolutions.com/blog/schedule-variance-versus-schedule-performance-index-pmp-concept-40
Author: | Mohammad Almohtaseb
(𝑬𝒂𝒓𝒏𝒆𝒅 𝑽𝒂𝒍𝒖𝒆)/(𝑷𝒍𝒂𝒏𝒏𝒆𝒅 𝑽𝒂𝒍𝒖𝒆)∗𝟏𝟎𝟎%
𝟓𝟎𝟎/𝟔𝟎𝟎∗𝟏𝟎𝟎%